## Ruiqi
| 2022 |  |  |  | 2023 |  |  |  | 2024 |  |  |  | 2025
module | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4
optimizer
optimization engine
productivity forecaster | bar: 2023 Q1
project simulator | bar: 2022 Q1 to 2022 Q4; 2023 Q2
project optimizer | bar: 2022 Q1 to 2022 Q4; 2023 Q3 to 2023 Q4
user input & optimization visualization
import / export module | bar: 2022 Q1 to 2023 Q1
control panel | bar: 2022 Q1 to 2023 Q1
optimization animator | bar: 2023 Q2
optimization summarizer & comparator | bar: 2022 Q1 to 2022 Q4; 2023 Q3
standard SaaS modules | bar: 2022 Q1 to 2023 Q4
designer (editor)
WBS editor | bar: 2024 Q1
tasks editor | bar: 2024 Q1
resources editor | bar: 2024 Q2
task-task relationship editor | bar: 2024 Q3
task-resource relationship editor | bar: 2024 Q3
cost editor | bar: 2024 Q4
executor
executor core | bar: 2025 Q1
executor comment system | bar: 2025 Q2
admin module | bar: 2025 Q3
adaptor module | bar: 2025 Q1 to 2025 Q4
developers
CTO | bar: 2022 Q1 to 2025 Q4
FE, frontend developer |  |  |  |  | 1 | 1 | 1 | 1 | 3 | 3 | 3 | 3 | 4 | 4 | 4 | 4
FS, full stack developer |  |  |  |  | 2 | 2 | 2 | 2 | 3 | 3 | 3 | 3 | 4 | 4 | 4 | 4
MD, mobile developer | 2025 Q1: 4; 2025 Q2: 4; 2025 Q3: 4; 2025 Q4: 4
BE, backend developer | 2024 Q1: 3; 2024 Q2: 3; 2024 Q3: 3; 2024 Q4: 3; 2025 Q1: 4; 2025 Q2: 4; 2025 Q3: 4; 2025 Q4: 4
AD, algorithm developer | 2024 Q1: 2; 2024 Q2: 2; 2024 Q3: 2; 2024 Q4: 2; 2025 Q1: 3; 2025 Q2: 3; 2025 Q3: 3; 2025 Q4: 3
total | 1 | 1 | 1 | 1 | 4 | 4 | 4 | 4 | 12 | 12 | 12 | 12 | 20 | 20 | 20 | 20

## Luis Edit
gray: things the CTO had to work on alone |  | yellow: after hiring
| 2022 |  |  |  | 2023 |  |  |  | 2024 |  |  |  | 2025
module | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4
optimizer
optimization engine
productivity forecaster | bar: 2022 Q4
project simulator | bar: 2022 Q1 to 2023 Q1
project optimizer
user input & optimization visualization
import / export module | bar: 2022 Q1 to 2023 Q1
control panel | bar: 2022 Q1 to 2023 Q1
optimization animator | bar: 2023 Q2
optimization summarizer & comparator | bar: 2022 Q1 to 2022 Q4; 2023 Q2
standard SaaS modules
designer (editor)
WBS editor | bar: 2023 Q3
tasks editor | bar: 2023 Q3
resources editor | bar: 2023 Q4
task-task relationship editor | bar: 2024 Q1
task-resource relationship editor | bar: 2024 Q1
cost editor | bar: 2024 Q2
executor
executor core | bar: 2024 Q3
executor comment system | bar: 2024 Q4
admin module | bar: 2024 Q3
adaptor module | bar: 2024 Q3 to 2025 Q2
developers
CTO | bar: 2022 Q1 to 2025 Q4
FE, frontend developer |  |  |  |  | 1 | 1 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3
FS, full stack developer |  |  |  |  | 2 | 2 | 2 | 2 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3
MD, mobile developer | 2024 Q3: 2; 2024 Q4: 2; 2025 Q1: 2; 2025 Q2: 2; 2025 Q3: 2; 2025 Q4: 2
BE, backend developer | [6 empty] | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2
AD, algorithm developer | 2024 Q1: 2; 2024 Q2: 2; 2024 Q3: 2; 2024 Q4: 2; 2025 Q1: 3; 2025 Q2: 3; 2025 Q3: 3; 2025 Q4: 3
total (excluding CTO) | 0 | 0 | 0 | 0 | 3 | 3 | 7 | 7 | 10 | 10 | 12 | 12 | 13 | 13 | 13 | 13